## Options (hidden)
Result | Main Menu | Access
O | System Access | User
Δ | Homepage | Curator
X | Maintenance | Admin
Transaction
Management Tools
Queries
Reports

## System Check #1
Main Module | Module | Access | Functionality | Result | Problem | Remarks | Date
System Access | System Access | User | OVERALL | X | Missing Functionality | Missing Functionality | 2019-05-04
System Access | System Access | User | Rotation of Image Set | O | None | Working As Expected | 2019-05-04
System Access | System Access | User | Login Form | O | None | Working As Expected | 2019-05-04
System Access | System Access | User | Validate Login Information | O | None | Working As Expected | 2019-05-04
System Access | System Access | User | Configure Database Connection | X | Missing Functionality | Missing Functionality | 2019-05-04
Homepage | Homepage | User | OVERALL | X | Missing Functionality | Missing Functionality | 2019-05-04
Homepage | Homepage | User | Welcome Banner | O | None | Working As Expected | 2019-05-04
Homepage | Homepage | User | Count for Herbarium Sheets | O | None | Working As Expected | 2019-05-04
Homepage | Homepage | User | Count for Verified Species | O | None | Working As Expected | 2019-05-04
Homepage | Homepage | User | Count for Available Boxes | O | None | Working As Expected | 2019-05-04
Homepage | Homepage | User | Count for Available Sheets for Loaning | O | None | Working As Expected | 2019-05-04
Homepage | Homepage | User | Count for New Deposits | O | None | Working As Expected | 2019-05-04
Homepage | Homepage | User | Count for Resubmitting Deposits | O | None | Working As Expected | 2019-05-04
Homepage | Homepage | User | Graph #1 (Pie Graph) | X | Indeterminate Data Set | Missing Functionality | 2019-05-04
Homepage | Homepage | User | Graph #2 (Bar Graph) | X | Indeterminate Data Set | Missing Functionality | 2019-05-04
Homepage | Homepage | User | Graph #3 (Line Graph) | X | Indeterminate Data Set | Missing Functionality | 2019-05-04
Homepage | Homepage | User | Graph #4 (Mixed Graph: Line + Bar) | X | Indeterminate Data Set | Missing Functionality | 2019-05-04
Maintenance | Taxonomic Hierarchy: Phylum | Curator | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Taxonomic Hierarchy: Phylum | Curator | View Phylum Table | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Phylum | Curator | Load Form (Add Phylum) | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Phylum | Curator | Load Form (Edit Phylum) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Phylum | Curator | Allow Default value for Domain & Kingdom | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Phylum | Curator | Auto-Suggest Phylum Name | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Phylum | Curator | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Phylum | Curator | Save New Phylum | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Phylum | Curator | Update Existing Phylum | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Class | Curator | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Taxonomic Hierarchy: Class | Curator | View Class Table | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Class | Curator | Load Form (Add Class) | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Class | Curator | Load Form (Edit Class) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Class | Curator | Drop-down List of Phyla | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Class | Curator | Auto-Suggest Class Name | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Class | Curator | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Class | Curator | Save New Class | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Class | Curator | Update Existing Class | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Order | Curator | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Taxonomic Hierarchy: Order | Curator | View Order Table | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Order | Curator | Load Form (Add Order) | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Order | Curator | Load Form (Edit Order) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Order | Curator | Drop-down List of Class | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Order | Curator | Auto-Suggest Order Name | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Order | Curator | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Order | Curator | Save New Order | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Order | Curator | Update Existing Order | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Family | Curator | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Taxonomic Hierarchy: Family | Curator | View Family Table | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Family | Curator | Load Form (Add Family) | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Family | Curator | Load Form (Edit Family) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Family | Curator | Drop-down List of Orders | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Family | Curator | Auto-Suggest Family Name | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Family | Curator | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Family | Curator | Save New Family | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Family | Curator | Update Existing Family | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Genus | Curator | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Taxonomic Hierarchy: Genus | Curator | View Genus Table | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Genus | Curator | Load Form (Add Genus) | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Genus | Curator | Load Form (Edit Genus) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Genus | Curator | Drop-down List of Families | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Genus | Curator | Auto-Suggest Genus Name | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Genus | Curator | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Genus | Curator | Save New Genus | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Genus | Curator | Update Existing Genus | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | OVERALL | Δ | Doubt of Access Level Refer to Plant Deposit | Doubt of Access Level Refer to Plant Deposit | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | View Species Table | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | Load Form (Add Species) | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | Load Form (Edit Species) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | Checkbox for Species Verification Status | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | Drop-down List of Genera | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | Drop-down List of Authors | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | Auto-Suggest Species Name | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | Save New Species | O | None | Working As Expected | 2019-04-17
Maintenance | Taxonomic Hierarchy: Species | Curator | Update Existing Species | O | None | Working As Expected | 2019-04-17
Maintenance | Species Author | Curator | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Species Author | Curator | View Species Author Table | O | None | Working As Expected | 2019-04-17
Maintenance | Species Author | Curator | Load Form (Add Species Author) | O | None | Working As Expected | 2019-04-17
Maintenance | Species Author | Curator | Load Form (Edit Species Author) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Species Author | Curator | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Species Author | Curator | Save New Species Author | O | None | Working As Expected | 2019-04-17
Maintenance | Species Author | Curator | Update Existing Species Author | O | None | Working As Expected | 2019-04-17
Maintenance | Species Basionym | Curator | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Species Basionym | Curator | View Species Basionym Table | O | None | Working As Expected | 2019-04-17
Maintenance | Species Basionym | Curator | Load Form (Add Species Basionym) | O | None | Working As Expected | 2019-04-17
Maintenance | Species Basionym | Curator | Load Form (Edit Species Basionym) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Species Basionym | Curator | Drop-down List of Species | O | None | Working As Expected | 2019-04-17
Maintenance | Species Basionym | Curator | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Species Basionym | Curator | Save New Species Basionym | O | None | Working As Expected | 2019-04-17
Maintenance | Species Basionym | Curator | Update Existing Species Basionym | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Types | User | OVERALL | X | Minor Fixes with Access Level [User] Not Included | Minor Fixes with Access Level [User] Not Included | 2019-04-17
Maintenance | Plant Types | User | View Plant Type Table | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Types | User | Load Form (Add Plant Type) | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Types | User | Load Form (Edit Plant Type) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Plant Types | User | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Plant Types | User | Save New Plant Type | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Types | User | Update Existing Plant Type | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Boxes | User | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Herbarium Boxes | User | View Herbarium Box Table | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Boxes | User | Load Form (Add Herbarium Box) | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Boxes | User | Load Form (Edit Herbarium Box) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Herbarium Boxes | User | Drop-down List of Families | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Boxes | User | Default Box Limit of 10 | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Boxes | User | Default Box Location Rack:1, Row:1, Column:1 | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Boxes | User | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Herbarium Boxes | User | Save New Herbarium Box | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Boxes | User | Update Existing Herbarium Box | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Plant Locality | User | View Locality Table | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | Load Form (Add Locality) | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | Load Form (Edit Locality) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Plant Locality | User | Drop-down List of Countries | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | Drop-down List of Provinces | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | Drop-down List of Cities by Provinces | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | Detailed Locality Fields for Philippines | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | Full Locality Field for Other Countries | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | Latitude and Longtitude format (Deg* Min' Sec" Dir) | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Plant Locality | User | Save New Locality | O | None | Working As Expected | 2019-04-17
Maintenance | Plant Locality | User | Update Existing Locality | O | None | Working As Expected | 2019-04-17
Maintenance | Collector | User | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Collector | User | View Collector Table | O | None | Working As Expected | 2019-04-17
Maintenance | Collector | User | Load Form (Add Collector) | O | None | Working As Expected | 2019-04-17
Maintenance | Collector | User | Load Form (Edit Collector) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Collector | User | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Collector | User | Save New Collector | O | None | Working As Expected | 2019-04-17
Maintenance | Collector | User | Update Existing Collector | O | None | Working As Expected | 2019-04-17
Maintenance | Borrower | User | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Borrower | User | View Borrower Table | O | None | Working As Expected | 2019-04-17
Maintenance | Borrower | User | Load Form (Add Borrower) | O | None | Working As Expected | 2019-04-17
Maintenance | Borrower | User | Load Form (Edit Borrower) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Borrower | User | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Borrower | User | Save New Borrower | O | None | Working As Expected | 2019-04-17
Maintenance | Borrower | User | Update Existing Borrower | O | None | Working As Expected | 2019-04-17
Maintenance | External Validator | Curator | OVERALL | X | Doubt of Access Level Refer to Plant Deposit | Doubt of Access Level Refer to Plant Deposit | 2019-04-17
Maintenance | External Validator | Curator | View External Validator Table | O | None | Working As Expected | 2019-04-17
Maintenance | External Validator | Curator | Load Form (Add External Validator) | O | None | Working As Expected | 2019-04-17
Maintenance | External Validator | Curator | Load Form (Edit External Validator) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | External Validator | Curator | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | External Validator | Curator | Save New External Validator | O | None | Working As Expected | 2019-04-17
Maintenance | External Validator | Curator | Update Existing External Validator | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Staff | Admin | OVERALL | O | Minor Fixes | Minor Fixes | 2019-04-17
Maintenance | Herbarium Staff | Admin | View Herbarium Staff Table | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Staff | Admin | Load Form (Add Herbarium Staff) | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Staff | Admin | Load Form (Edit Herbarium Staff) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Herbarium Staff | Admin | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Herbarium Staff | Admin | Save New Herbarium Staff | O | None | Working As Expected | 2019-04-17
Maintenance | Herbarium Staff | Admin | Update Existing Herbarium Staff | O | None | Working As Expected | 2019-04-17
Maintenance | Access Accounts | Admin | OVERALL | X | Minor Fixes with Missing Functionality | Minor Fixes with Missing Functionality | 2019-04-17
Maintenance | Access Accounts | Admin | View Active Access Accounts Table | O | None | Working As Expected | 2019-04-17
Maintenance | Access Accounts | Admin | Load Form (Add Access Accounts) | O | None | Working As Expected | 2019-04-17
Maintenance | Access Accounts | Admin | Load Form (Edit Access Accounts) | Δ | Update Record is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Access Accounts | Admin | Deactivate Access Account | X | Missing Functionality | Missing Functionality | 2019-04-17
Maintenance | Access Accounts | Admin | Drop-down List of Herbarium Staffs | O | None | Working As Expected | 2019-04-17
Maintenance | Access Accounts | Admin | Clear Form | Δ | Changes Update Record to Insert Record | Working Fine No Exceptions Occur | 2019-04-17
Maintenance | Access Accounts | Admin | Save New Herbarium Staff | O | None | Working As Expected | 2019-04-17
Maintenance | Access Accounts | Admin | Update Existing Herbarium Staff | O | None | Working As Expected | 2019-04-17
Transaction | Plant Deposit | User | OVERALL | X | Working with Missing Functionality | Working with Missing Functionality | 2019-05-04
Transaction | Plant Deposit | User | New Deposit Form | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Existing Deposit Form (Verified & Unverified) | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Toggle Verified Deposit Status | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Load Photo from File | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Capture Photo thru Available Webcam | X | Missing Functionality | Missing Functionality | 2019-05-04
Transaction | Plant Deposit | User | Drop-down List of Plant Types | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Drop-down List of Plant Taxon (Scientific Name) | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Drop-down List of Collectors | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Drop-down List of Internal & External Validators | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Drop-down List of Localities | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Add New Plant Type (if not exists) | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Add Taxon Species (if not exists) | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Add New Collector (if not exists) | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Add New External Validator (if not exists) | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Add New Locality (if not exists) | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Checkbox for Plant Deposit Condition | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Clear Form | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Save New Deposit | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Save Existing Unverified Deposit | O | None | Working As Expected | 2019-05-04
Transaction | Plant Deposit | User | Save Existing Verified Deposit | O | None | Working As Expected | 2019-05-04
Transaction | Plant Receiving | Curator | OVERALL | O | Minor Fixes | Minor Fixes | 2019-05-04
Transaction | Plant Receiving | Curator | View New Plant Deposit Table | O | None | Working As Expected | 2019-05-04
Transaction | Plant Receiving | Curator | Load Confirm Deposit Form | Δ | Transaction is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-05-04
Transaction | Plant Receiving | Curator | Load Plant Deposit Photo | O | None | Working As Expected | 2019-05-04
Transaction | Plant Receiving | Curator | Load Plant Deposit Information | O | None | Working As Expected | 2019-05-04
Transaction | Plant Receiving | Curator | Accept Plant Deposit | O | None | Working As Expected | 2019-05-04
Transaction | Plant Receiving | Curator | Reject Plant Deposit | O | None | Working As Expected | 2019-05-04
Transaction | Plant Resubmission | User | OVERALL | O | Minor Fixes | Minor Fixes | 2019-05-04
Transaction | Plant Resubmission | User | View Rejected Plant Deposit Table | O | None | Working As Expected | 2019-05-04
Transaction | Plant Resubmission | User | Load Resubmit Deposit Form | Δ | Transaction is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-05-04
Transaction | Plant Resubmission | User | Load Plant Deposit Photo | O | None | Working As Expected | 2019-05-04
Transaction | Plant Resubmission | User | Load Plant Deposit Information | O | None | Working As Expected | 2019-05-04
Transaction | Plant Resubmission | User | Upload Photo from File | O | None | Working As Expected | 2019-05-04
Transaction | Plant Resubmission | User | Drop-down List of Plant Types | O | None | Working As Expected | 2019-05-04
Transaction | Plant Resubmission | User | Drop-down List of Localities | O | None | Working As Expected | 2019-05-04
Transaction | Plant Resubmission | User | Checkbox for Plant Deposit Condition | O | None | Working As Expected | 2019-05-04
Transaction | Plant Resubmission | User | Update Plant Deposit Information | O | None | Working As Expected | 2019-05-04
Transaction | Plant Resubmission | User | Submit Plant Deposit | Δ | Herbarium Photo Auto-Removes when Not Update | Working Fine No Exceptions Occur | 2019-05-04
Transaction | Plant Verification | User | OVERALL | X | Minor Fixes with Access Level [User] Not Included | Minor Fixes with Access Level [User] Not Included | 2019-05-04
Transaction | Plant Verification | User | View Unverified Herbarium Sheet Table | O | None | Working As Expected | 2019-05-04
Transaction | Plant Verification | User | Load Verify Deposit Form | Δ | Transaction is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-05-04
Transaction | Plant Verification | User | Load Herbarium Sheet Photo | O | None | Working As Expected | 2019-05-04
Transaction | Plant Verification | User | Load Herbarium Sheet Information | O | None | Working As Expected | 2019-05-04
Transaction | Plant Verification | User | Drop-down List of Plant Taxon (Scientific Name) | O | None | Working As Expected | 2019-05-04
Transaction | Plant Verification | User | Drop-down List of Internal & External Validators | O | None | Working As Expected | 2019-05-04
Transaction | Plant Verification | User | Drop-down List of Accession Numbers by Taxon | O | None | Working As Expected | 2019-05-04
Transaction | Plant Verification | User | Checkbox if Herbarium Sheet is Duplicate | O | None | Working As Expected | 2019-05-04
Transaction | Plant Verification | User | Verify Herbarium Sheet | O | None | Working As Expected | 2019-05-04
Transaction | Plant Verification | User | Further Verify Herbarium Sheet | O | None | Working As Expected | 2019-05-04
Transaction | Plant Classification | User | OVERALL | O | Minor Fixes | Minor Fixes | 2019-05-04
Transaction | Plant Classification | User | View Verified Herbarium Sheet Table | O | None | Working As Expected | 2019-05-04
Transaction | Plant Classification | User | Load Classify Sheet Form | Δ | Transaction is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-05-04
Transaction | Plant Classification | User | Load Herbarium Sheet Photo | O | None | Working As Expected | 2019-05-04
Transaction | Plant Classification | User | Load Herbarium Sheet Information | O | None | Working As Expected | 2019-05-04
Transaction | Plant Classification | User | Set Herbarium Box Location | O | None | Working As Expected | 2019-05-04
Transaction | Plant Classification | User | Toggle Herbarium Sheet Availability for Loaning | O | None | Working As Expected | 2019-05-04
Transaction | Plant Classification | User | Classify and Store Herbarium Sheet | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | OVERALL | X | Minor Fixes with Missing Functionality | Minor Fixes with Missing Functionality | 2019-05-04
Transaction | Plant Loaning | User | View Current Plant Loan Table | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | Load Form (New Loan) | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | Load Form (View Loan) | Δ | Transaction is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-05-04
Transaction | Plant Loaning | User | Load Form (Return Loaned Sheets) | Δ | Transaction is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-05-04
Transaction | Plant Loaning | Curator | Load Form (Approve Loan) | X | Missing Functionality | Missing Functionality | 2019-05-04
Transaction | Plant Loaning | User | (New Loan) Drop-down List of Borrowers + Collectors | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (New Loan) List of Taxon Families | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (New Loan) List of Taxon Genera by Family | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (New Loan) List of Taxon Species by Genus | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (New Loan) Set Copies to 1 | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (View Loan) Load Plant Loan Information | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (View Loan) Load Loaned Species | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (View Loan) Load Loaned Specimens | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (Return Loan) Load Plant Loan Information | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (Return Loan) Load Loaned Species | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (Return Loan) Load Loaned Specimens | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | (Return Loan) Set Plant Status as Undamaged | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | Curator | (Approve Loan) Load Plant Loan Information | X | Missing Functionality | Missing Functionality | 2019-05-04
Transaction | Plant Loaning | Curator | (Approve Loan) Load Loaned Species | X | Missing Functionality | Missing Functionality | 2019-05-04
Transaction | Plant Loaning | Curator | (Approve Loan) Load Loaned Specimens | X | Missing Functionality | Missing Functionality | 2019-05-04
Transaction | Plant Loaning | User | (New Loan) Clear Form | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | Process New Loan | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | User | Return Loaned Sheets | O | None | Working As Expected | 2019-05-04
Transaction | Plant Loaning | Curator | Approve New Loan | X | Missing Functionality | Missing Functionality | 2019-05-04
Transaction | Plant Loaning | Curator | Reject New Loan | X | Missing Functionality | Missing Functionality | 2019-05-04
Management Tools | Herbarium Inventory | User | OVERALL | X | Minor Fixes with Missing Functionality | Minor Fixes with Missing Functionality | 2019-05-04
Management Tools | Herbarium Inventory | User | View Herbarium Box List | O | None | Working As Expected | 2019-05-04
Management Tools | Herbarium Inventory | User | View Herbarium Inventory by Family Box | O | None | Working As Expected | 2019-05-04
Management Tools | Herbarium Inventory | User | Load Form (View Herbarium Sheet) | Δ | Transaction is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-05-04
Management Tools | Herbarium Inventory | User | Load Form (Update Herbarium Sheet) | Δ | Transaction is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-05-04
Management Tools | Herbarium Inventory | User | Load Form (Update Herbarium Picture) | X | Missing Functionality | Missing Functionality | 2019-05-04
Management Tools | Herbarium Inventory | User | (View Sheet) Load Herbarium Sheet Photos | Δ | Tag Unreadable | Working Fine No Exceptions Occur | 2019-05-04
Management Tools | Herbarium Inventory | User | (View Sheet) Load Herbarium Sheet Information | O | None | Working As Expected | 2019-05-04
Management Tools | Herbarium Inventory | User | (Update Sheet) Load Herbarium Sheet Photos | Δ | Tag Unreadable | Working Fine No Exceptions Occur | 2019-05-04
Management Tools | Herbarium Inventory | User | (Update Sheet) Load Herbarium Sheet Information | O | None | Working As Expected | 2019-05-04
Management Tools | Herbarium Inventory | User | (Update Sheet) List of Herbarium Boxes by Family | O | None | Working As Expected | 2019-05-04
Management Tools | Herbarium Inventory | User | Set Herbarium Box Location | O | None | Working As Expected | 2019-05-04
Management Tools | Herbarium Inventory | User | Toggle Herbarium Sheet Availability for Loaning | O | None | Working As Expected | 2019-05-04
Management Tools | Herbarium Inventory | User | Update Herbarium Sheet | O | None | Working As Expected | 2019-05-04
Management Tools | Sheet Tracking | User | OVERALL | O | Minor Fixes | Minor Fixes | 2019-05-04
Management Tools | Sheet Tracking | User | View Herbarium Sheets with Current Transaction | O | None | Working As Expected | 2019-05-04
Management Tools | Sheet Tracking | User | Load Herbarium Sheet Form | Δ | Transaction is accessible when no record is selected | Working Fine No Exceptions Occur | 2019-05-04
Management Tools | Sheet Tracking | User | Load Herbarium Sheet Information | O | None | Working As Expected | 2019-05-04
Management Tools | Sheet Tracking | User | Load Herbarium Sheet Photos | Δ | Only Primary Sheet Displayed | Working Fine No Exceptions Occur | 2019-05-04
Management Tools | Sheet Tracking | User | Load Herbarium Sheet Status & Current Location | O | None | Working As Expected | 2019-05-04
Management Tools | Audit Trailing | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Management Tools | Audit Trailing | Curator | View Processed Transactions | O | None | Working As Expected | 2019-05-04
Management Tools | Audit Trailing | Curator | Load Transaction Information | O | None | Working As Expected | 2019-05-04
Management Tools | Audit Trailing | Curator | Load Affected Herbarium Sheet | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Queries | Taxon Species | Curator | Drop-down List of Categories for Taxon Species | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | Check List of Taxon Phylum | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | Check List of Taxon Class | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | Check List of Taxon Order | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | Check List of Taxon Family | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | Check List of Taxon Genus | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | Check List of Species Author | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | View Taxon Species by Selected Criteria | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | Load Taxon Species Information | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | Search Taxon Species | O | None | Working As Expected | 2019-05-04
Queries | Taxon Species | Curator | Clear Filters | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Queries | Herbarium Sheet | Curator | Drop-down List of Categories for Herbarium Sheets | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | Check List of Taxon Species | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | Check List of Plant Types | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | Check List of Province | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | Check List of Collector | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | Check List of Herbarium Box | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | Check List of Specimen Status | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | View Herbarium Sheets by Selected Criteria | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | Load Herbarium Sheet Information | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | Search Herbarium Sheet | O | None | Working As Expected | 2019-05-04
Queries | Herbarium Sheet | Curator | Clear Filters | O | None | Working As Expected | 2019-05-04
Reports | New Deposits | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Reports | New Deposits | Curator | Drop-down Filter by Month | O | None | Working As Expected | 2019-05-04
Reports | New Deposits | Curator | Load Herbarium Sheet Table by Filter | O | None | Working As Expected | 2019-05-04
Reports | New Deposits | Curator | Print Report | O | None | Working As Expected | 2019-05-04
Reports | Rejected Deposits | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Reports | Rejected Deposits | Curator | Drop-down Filter by Month | O | None | Working As Expected | 2019-05-04
Reports | Rejected Deposits | Curator | Load Herbarium Sheet Table by Filter | O | None | Working As Expected | 2019-05-04
Reports | Rejected Deposits | Curator | Print Report | O | None | Working As Expected | 2019-05-04
Reports | Verified Deposits | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Reports | Verified Deposits | Curator | Drop-down Filter by Month | O | None | Working As Expected | 2019-05-04
Reports | Verified Deposits | Curator | Load Herbarium Sheet Table by Filter | O | None | Working As Expected | 2019-05-04
Reports | Verified Deposits | Curator | Print Report | O | None | Working As Expected | 2019-05-04
Reports | Externally Verified Deposits | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Reports | Externally Verified Deposits | Curator | Load Herbarium Sheet Table | O | None | Working As Expected | 2019-05-04
Reports | Externally Verified Deposits | Curator | Print Report | O | None | Working As Expected | 2019-05-04
Reports | Damaged Sheets by Collector | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Reports | Damaged Sheets by Collector | Curator | Drop-down Filter by Collector | O | None | Working As Expected | 2019-05-04
Reports | Damaged Sheets by Collector | Curator | Load Herbarium Sheet Table by Filter | O | None | Working As Expected | 2019-05-04
Reports | Damaged Sheets by Collector | Curator | Print Report | O | None | Working As Expected | 2019-05-04
Reports | Damaged Sheets by Loan Nos. | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Reports | Damaged Sheets by Loan Nos. | Curator | Drop-down Filter by Loan Number | O | None | Working As Expected | 2019-05-04
Reports | Damaged Sheets by Loan Nos. | Curator | Load Herbarium Sheet Table by Filter | O | None | Working As Expected | 2019-05-04
Reports | Damaged Sheets by Loan Nos. | Curator | Print Report | O | None | Working As Expected | 2019-05-04
Reports | Damaged Sheets by Month | Curator | OVERALL | O | None | Working Fine | 2019-05-04
Reports | Damaged Sheets by Month | Curator | Drop-down Filter by Month | O | None | Working As Expected | 2019-05-04
Reports | Damaged Sheets by Month | Curator | Load Herbarium Sheet Table by Filter | O | None | Working As Expected | 2019-05-04
Reports | Damaged Sheets by Month | Curator | Print Report | O | None | Working As Expected | 2019-05-04
Legend:
|  |  | Working Fine | O
|  |  | Working with Non-Fatal Exception / Logic Problem | Δ
|  |  | Not Working with No Functionality / Fatal Exception | X